## Sheet1
Team A1 - Scrum Sprint 0 - Start Date: September 17, 2021 - End Date: September 30, 2021
Task ID | Backlog Item | Task Description | Estimated Time (Hours) | Actual Time (Hours) | Pre-Requisite | Team Member(s) | Success Criteria | Due Date | Obstacles | Status
GIT-1 | n/a | Create Git Repository | 0.5 | 0.5 | none | Matthew Merritt | Git repository is successfully created and can be accessed on GitHub. | 2021-09-25 |  | Completed
US-1 | n/a | Write user story for menu navigation enhancement | 1 | 1 | none | Amber Kusma | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-1 | n/a | Create test case for menu navigation enhancement | 1 | 1 | none | Amber Kusma | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-2 | n/a | Write user story instructions and credits screen enhancement | 1 | 1 | none | Amber Kusma | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-2 | n/a | Create test case instructions and credits screen enhancement | 1 | 1 | none | Amber Kusma | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-3 | n/a | Write user story for "A" key crashing bug | 1 | 1 | none | Priscilla Esteves | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-3 | n/a | Create test case for "A" key crashing bug | 1 | 1 | none | Priscilla Esteves | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-4 | n/a | Write user story for repeating sound bug | 1 | 1 | none | Matthew Merritt | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-4 | n/a | Create test case for repeating sound bug | 1 | 1 | none | Matthew Merritt | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-5 | n/a | Write user story for enemy collision bug | 1 | 1 | none | Matthew Merritt | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-5 | n/a | Create test case for enemy collision bug | 1 | 1 | none | Matthew Merritt | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-6 | n/a | Write user story for invisible attack bug | 1 | 1 | none | Dylan Widecki | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-6 | n/a | Create test case for Invisible attack bug | 1 | 1 | none | Dylan Widecki | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-7 | n/a | Write user story for removing inescapable areas enhancement | 1 | 1 | none | Emily Balboni | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-7 | n/a | Create test case for removing inescapable areas enhancement | 1 | 1 | none | Emily Balboni | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-8 | n/a | Write user story for level 5 redesign enhancement | 1 | 1 | none | Emily Balboni | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-8 | n/a | Create test case for level 5 redesign enhancement | 1 | 1 | none | Emily Balboni | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-9 | n/a | Write user story for theme enhancement | 1 | 1 | none | Priscilla Esteves | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-9 | n/a | Create test case for theme enhancement | 1 | 1 | none | Priscilla Esteves | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
US-10 | n/a | Write user story for water functionality bug | 1 | 1 | none | Dylan Widecki | User story is read and approved by all members of the team. | 2021-09-25 |  | Completed
TC-10 | n/a | Create test case for water functionality bug | 1 | 1 | none | Dylan Widecki | Test case is read and approved by all members of the team. | 2021-09-25 |  | Completed
PR-1 | n/a | Create presentation and report | 5 | 7 | all above items | Amber Kusma, Priscilla Esteves, Matthew Merritt, Emily Balboni, and Dylan Widecki | The team has a completed presentation and report that has been checked with the rubric, and the team has completed multiple practice runs of the presentation. | 2021-09-29 |  | Completed
|  | Total: | 25.5 | 27.5
Team A1 - Scrum Sprint 1 - Start Date: October 1, 2021 - End Date: October 14, 2021
Task ID | Backlog Item | Task Description | Estimated Time (Hours) | Actual Time (Hours) | Pre-Requisite | Team Member(s) | Success Criteria | Due Date | Obstacles | Status
MN-1 | A - Menu Navigation | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Dylan and Priscilla | Test Case Steps Understood | 2021-10-07 |  | Completed
MN-2 | A | Find User Movement In Code | 0.25 | 0.25 |  | Dylan and Priscilla | Correct Code is Located | 2021-10-08 |  | Completed
MN-3 | A | Add Mouse Input to Menu | 2 | 2.5 | MN-2 | Dylan Widecki | M01 | 2021-10-08 |  | Completed
MN-4 | A | Add Extra Buttons | 2 | 1.5 | MN - 3 | Priscilla Esteves | M01 | 2021-10-11 |  | Completed
MN-5 | A | Fill out Test Case | 0.25 | 0.25 | MN-3, MN-4 | Dylan and Priscilla | M01 | 2021-10-11 |  | Completed
IC - 1 | B - Instructions and Credit Screen | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Amber and Emily | Test Case Steps Understood | 2021-10-07 |  | Completed
IC - 2 | B | Re-word instructions | 1 | 0.5 |  | Amber Kusma | M02 | 2021-10-11 |  | Completed
IC - 3 | B | Fix Spacing on Credits | 1 | 0.5 |  | Emily Balboni | M02 | 2021-10-11 |  | Completed
IC - 4 | B | Fill out Test Case | 0.25 | 0.1 | IC - 1 | Amber and Emily | M02 | 2021-10-11 |  | Completed
A-1 | C - A Key Crashing | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Matthew Merritt | Test Case Steps Understood | 2021-10-07 |  | Completed
A-2 | C | Find A Key Bug in Code | 1 | 2.5 |  | Matthew Merritt | Correct Code is Located | 2021-10-11 |  | Completed
A-3 | C | Fix Bug where 'A' key crashes game | 4.5 | 1 | A-2 | Matthew Merritt | C03 | 2021-10-11 |  | Completed
A-4 | C | Fill out Test Case | 0.25 | 0.25 | A-3 | Matthew Merritt | C03 | 2021-10-11 |  | Completed
SM-1 | n/a | Write Notable System Improvement | 0.5 | 0.5 |  | Matthew Merritt | Team and Manager sign document | 2021-10-05 |  | Completed
SM-2 | n/a | Merge Branches | 1 | 1 |  | Matthew and Priscilla | All branches with active changes are merged | 2021-10-12 |  | Completed
R-1 | n/a | Create Presentation | 3 | 4 |  | Whole Team | Team completes multiple practice runs | 2021-10-13 |  | Completed
R-2 | n/a | Update Backlog | 0.5 | 0.5 |  | Matthew Merritt | Backlog contains all prioritized bugs and enhancements, and completed items are moved to a separate list | 2021-10-13 |  | Completed
R-3 | n/a | Individual Postmortems | 0.5 | 0.5 |  | Whole Team | Postmortems meet requirements from the rubric and is visible in OneDrive | 2021-10-15 |  | Completed
R-4 | n/a | Team Postmortem | 0.5 | 0.5 |  | Matthew Merritt | Postmortems meet requirements from the rubric and is visible in OneDrive | 2021-10-15 |  | Completed
|  | Total: | 19.25 | 17.1
Team A1 - Scrum Sprint 2 - Start Date: October 15, 2021 - End Date: October 28, 2021
Task ID | Backlog Item | Task Description | Estimated Time (Hours) | Actual Time (Hours) | Pre-Requisite | Team Member(s) | Success Criteria | Due Date | Obstacles | Status
S-1 | D - Repeating Sound | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Matthew Merritt | Test case S04 passes | 2021-10-21 |  | Completed
S-2 | D | Find powerup sound and powerup state in code | 3 | 1 | S-1 | Matthew Merritt | Test case S04 passes | 2021-10-23 |  | Completed
S-3 | D | Implement sound fix so it plays only once | 1.5 | 0.5 | S-2 | Matthew Merritt | Test case S04 passes | 2021-10-24 |  | Completed
S-4 | D | Fill out test case | 0.25 | 0.25 | S-3 | Amber Kusma | Test case S04 passes | 2021-10-25 |  | Completed
IA-1 | E - Removing Inescapable Areas | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Amber Kusma | Test case L07 passes | 2021-10-21 |  | Completed
IA-2 | E | Find the code for the inescapable areas | 1 | 1.5 | IA-1 | Amber Kusma | Test case L07 passes | 2021-10-23 |  | Completed
IA-3 | E | Change the height of the obstacles so players can jump over them | 0.5 | 0.5 | IA-2 | Amber Kusma | Test case L07 passes | 2021-10-24 |  | Completed
IA-4 | E | Fill out test case | 0.25 | 0.5 | IA-3 | Emily Balboni | Test case L07 passes | 2021-10-25 | There were two inescapable areas in level 3 instead of just the 1. I edited the test case, that I wrote in a previous scrum sprint to update it appropriately. | Completed
ATK-1 | F - Invisible Attack Bug | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Emily Balboni | Test case A06 passes | 2021-10-21 |  | Completed
ATK-2 | F | Find the collision with the purple flower | 1 | 1 | ATK-1 | Emily Balboni | Test case A06 passes | 2021-10-23 |  | Completed
ATK-3 | F | Implement a fix so the powerup works when collected | 1.5 | 0.5 | ATK-2 | Emily Balboni | Test case A06 passes | 2021-10-24 | I originally edited only two lines of the code, it was brought to my attention that I did missed two other lines so I ended up doing two pull requests. | Completed
ATK-4 | F | Fill out test case | 0.25 | 0.25 | ATK - 3 | Priscilla Esteves | Test case A06 passes | 2021-10-25 |  | Completed
EC-1 | G- Enemy Collision | Go through Test Case | 0.25 | 1 | Create Test Case | Priscilla Esteves | Test case A05 passes | 2021-10-21 |  | Completed
EC-2 | G | Find the collision with the players and enemy | 0.25 | 3 | EC-1 | Priscilla Esteves, Matthew Merritt | Test case A05 passes | 2021-10-23 | The code handling the collision and bounds checking was difficult to track down. | Completed
EC-3 | G | Create a fix where enemy are defeated easily with only one attack | 1 | 1 | EC-2 | Priscilla Esteves, Matthew Merritt | Test case A05 passes | 2021-10-24 |  | Completed
EC-4 | G | Fill out test case | 0.25 | 0.25 | EC-3 | Dylan Widecki | Test case A05 passes | 2021-10-25 |  | Completed
T-1 | H - Theme Enhancement | Go Through Test Case | 0.25 | 0.25 | Create Test Case | Dylan Widecki | Test case T09 passes | 2021-10-21 |  | Completed
T-2 | H | Find the dinosaur, bug, fireball, purple flower and gold box in code | 0.75 | 0.75 | T-1 | Dylan Widecki | Test case T09 passes | 2021-10-21 |  | Completed
T-3 | H | Draw a new sprite for dinosaur, bug, fireball, purple flower and goldbox in MS Paint | 1.5 | 1 | T-2 | Dylan Widecki | Test case T09 passes | 2021-10-23 |  | Completed
T-4 | H | Change the appearance of the dinosaur, bug, fireball and gold box with new images | 0.5 | 1 | T-3 | Dylan Widecki | Test case T09 passes | 2021-10-24 |  | Completed
T-8 | H | Fill out test case | 0.25 | 0.25 | T-3 | Matthew Merritt | Test case T09 passes | 2021-10-25 | The enemy types have been changed since the test case was written and it needed to be updated. | Completed
SM-1 | n/a | Write Notable System Improvement | 0.5 | 0.5 | Backlog Items Selected | Matthew Merritt | Team and Manager sign document | 2021-10-19 |  | Completed
SM-2 | n/a | Merge Branches | 1 | 1.5 | S-4, IA-4, ATK-4, EC-4, T-6 | Matthew Merritt | All active branches are merged into master branch | 2021-10-25 | A couple features needed to be modified to meet requirements before they were fully merged. | Completed
R-1 | n/a | Create Presentation | 3 | 3 | SM-2 | Whole Team | Team completes multiple practice runs | 2021-10-27 |  | Completed
R-2 | n/a | Update Backlog | 0.5 | 0.5 | SM-2 | Matthew Merritt | Backlog contains all prioritized bugs and enhancements, and completed items are moved to a separate list | 2021-10-27 |  | Completed
R-3 | n/a | Write Individual Postmortems | 0.5 | 0.5 | Presentation | Whole Team | Postmortems meet requirements from the rubric and are visible in OneDrive | 2021-10-28 |  | Completed
R-4 | n/a | Write Team Postmortem | 0.5 | 0.5 | Presentation | Matthew Merritt | Postmortems meet requirements from the rubric and are visible in OneDrive | 2021-10-29 |  | Completed
MN-6 | A - Menu Navigation | Find code for highlighting menu options in screens | 0.5 | 0.5 | MN-5 | Matthew Merritt | Test case M01 passes | 2021-10-24 |  | Completed
MN-7 | A | Add highlight when hovering on the buttons in menu, instructions, and credits screens | 2 | 2 | MN-6 | Matthew Merritt | Test case M01 passes | 2021-10-25 |  | Completed
MN-8 | A | Fill out test case | 0.25 | 0.25 | MN-7 | Amber Kusma | Test case M01 passes | 2021-10-25 |  | Completed
|  | Total Times: | 23.75 | 24.5
Team A1 - Scrum Sprint 3 - Start Date: October 29, 2021 - End Date: November 11, 2021
Task ID | Backlog Item | Task Description | Estimated Time (Hours) | Actual Time (Hours) | Pre-Requisite | Team Member(s) | Success Criteria | Due Date | Obstacles | Status
LR-1 | I - Level 5 Redesign | Read through test case | 0.25 | 0.25 | Create test case | Amber Kusma | Test case L08 passes | 2021-11-04 |  | Completed
LR-2 | I | Find code for level 5 | 1 | 1 | LR-1 | Amber Kusma | Test case L08 passes | 2021-11-06 |  | Completed
LR-3 | I | Implement code to redesign level | 2 | 2.5 | LR-2 | Amber Kusma | Test case L08 passes | 2021-11-07 |  | Completed
LR-4 | I | Fill out Test Case | 0.25 | 0.25 | LR-3 | Dylan Widecki | Test case L08 passes | 2021-11-08 |  | Completed
W-1 | J - Water Functionality Bug | Read through test case | 0.25 | 0.25 | Create test case | Dylan Widecki | Test case W10 passes | 2021-11-04 |  | Completed
W-2 | J | Find code for water tiles and tile functionality | 1 | 2 | W-1 | Dylan Widecki | Test case W10 passes | 2021-11-05 |  | Completed
W-3 | J | Implement fixes to water functionality code | 2 | 0.5 | W-2 | Dylan Widecki | Test case W10 passes | 2021-11-07 |  | Completed
W-4 | J | Fill out Test Case | 0.25 | 0.25 | W-3 | Priscilla Esteves | Test case W10 passes | 2021-11-08 |  | Completed
AN-1 | K - Animation Issues Bug | Create Test Case | 0.25 | 0.25 | Team Discussion | Priscilla Esteves | Test case is created and added to repository | 2021-11-04 |  | Completed
AN-2 | K | Read through Test Case | 0.25 | 0.25 | Create test case | Priscilla Esteves | Test case created for AN-1 passes | 2021-11-04 |  | Completed
AN-3 | K | Find code for Animation Issues | 1 | 2 | AN-1 | Priscilla Esteves | Test case created for AN-1 passes | 2021-11-05 |  | Completed
AN-4 | K | Implment fixes for animation functionality | 1 | 2 | AN-2 | Priscilla Esteves | Test case created for AN-1 passes | 2021-11-07 |  | Completed
AN-5 | K | Fill out Test Case | 0.25 | 0.25 | AN-3 | Emily Balboni | Test case created for AN-1 passes | 2021-11-08 |  | Completed
MB-1 | L - Mute Button Enhancement | Create a Test Case | 0.25 | 0.25 | Team Discussion | Emily Balboni | Test case is created and added to repository | 2021-11-04 |  | Completed
MB-2 | L | Read through test case | 0.25 | 0.25 | Create test case | Emily Balboni | Test case created for MB-1 passes | 2021-11-04 |  | Completed
MB-3 | L | Look through code for music states | 0.5 | 0.5 | MB - 2 | Emily Balboni | Test case created for MB-1 passes | 2021-11-06 |  | Completed
MB-4 | L | Create a button on the screen | 0.5 | 1 | MB-3 | Emily Balboni | Test case created for MB-1 passes | 2021-11-07 | Took longer than expected to draw the image in paint application and load it into the resources fill. Also ran into difficulty adjusting the image size. | Completed
MB-5 | L | Add conditionals so when pressed sounds stops/ starts | 0.5 | 0.5 | MB-4 | Emily Balboni | Test case created for MB-1 passes | 2021-11-07 |  | Completed
MB-6 | L | Look through keyboard inputs | 0.25 | 0.25 | MB-5 | Emily Balboni | Test case created for MB-1 passes | 2021-11-07 |  | Completed
MB-7 | L | Create a condition when a specific key is pressed sounds stops/starts | 0.5 | 0.5 | MB-6 | Emily Balboni | Test case created for MB-1 passes | 2021-11-07 |  | Completed
MB-8 | L | Fill out Test Case | 0.25 | 0.25 | MB-7 | Matthew Merritt | Test case created for MB-1 passes | 2021-11-08 |  | Completed
LA-1 | M - Lingering Attack Bug | Create Test Case | 0.25 | 0.25 | Team Discussion | Matthew Merritt | Test case created and added to repository | 2021-11-04 |  | Completed
LA-2 | M | Go Through Test Case | 0.25 | 0.25 | LA-1 | Matthew Merritt | Test case created for task LA-1 passes | 2021-11-04 |  | Completed
LA-3 | M | Find code to delete and spawn the player's projectiles | 1 | 2 | LA-2 | Matthew Merritt | Test case created for task LA-1 passes | 2021-11-06 | The issue was not what we initially thought, and I needed to look at the way the player checked fireball collisions rather than how fireballs were removed. | Completed
LA-4 | M | Implement a fix to properly delete projectiles and the hitboxes when they disappear | 2 | 1 | LA-3 | Matthew Merritt | Test case created for task LA-1 passes | 2021-11-07 |  | Completed
LA-5 | M | Fill out Test Case | 0.25 | 0.25 | LA-4 | Amber Kusma | Test case created for task LA-1 passes | 2021-11-08 |  | Completed
AN-7 | K | Find code that is causing the player to move faster while shooting | 0.5 | 1 | AN-4 | Priscilla Esteves, Matthew Merritt | Test case created for AN-1 passes | 2021-11-10 | The bug appeared to be the result of the previous player state not being tracked properly, but it was unclear how this can be modified without impacting other features. | Completed
AN-6 | K | Fix new bug that is causing the player to move quicker when attacking | 0.5 | 1 | AN-6 | Priscilla Esteves, Matthew Merritt | Test case created for AN-1 passes | 2021-11-10 | The movement was fixed, but the attack feature had to be modified to only fire a single projectile when space is held. | Completed
SM-1 | n/a | Write Notable System Improvement | 0.5 | 0.5 | Backlog Items Selected | Matthew Merritt | Team and Manager sign document | 2021-11-02 |  | Completed
SM-2 | n/a | Merge Branches | 1 | 1.25 | LR-4, W-4, AN-5, MB-8, LA-5 | Matthew Merritt | All active branches are merged into master branch | 2021-11-08 | A couple of features needed additional development before being merged. | Completed
R-1 | n/a | Create Presentation Slides Individually | 1 | 1 | SM-2 | Whole Team | All slides are visible in the shared PowerPoint Presentation | 2021-11-10 |  | Completed
R-2 | n/a | Practice Presentation as Team | 1 | 1.5 | R-1 | Whole Team | Team completes multiple practice runs | 2021-11-10 |  | Completed
R-3 | n/a | Update Backlog | 0.5 | 0.5 | SM-2 | Matthew Merritt | Backlog contains all prioritized bugs and enhancements, and completed items are moved to a separate list | 2021-11-10 |  | Completed
R-3 | n/a | Write Individual Postmortems | 0.5 | 0.5 | Presentation | Whole Team | Postmortems meet requirements from the rubric and are visible in OneDrive | 2021-11-11 |  | Completed
R-4 | n/a | Write Team Postmortem | 0.5 | 0.5 | Presentation | Matthew Merritt | Postmortems meet requirements from the rubric and are visible in OneDrive | 2021-11-12 |  | Completed
|  | Total Times: | 22.5 | 26.75
Team A1 - Scrum Sprint 4 - Start Date: November 12, 2021 - End Date: December 2, 2021
Task ID | Backlog Item | Task Description | Estimated Time (Hours) | Actual Time (Hours) | Pre-Requisite | Team Member(s) | Success Criteria | Due Date | Obstacles | State
AD-1 | L - Attack Duration Bug | Create Test Case | 0.25 | 0.25 | Team Discussion | Matthew Merritt | Test case is created and added to repository | 2021-11-18 |  | Completed
AD-2 | L | Go Through Test Case | 0.25 | 0.25 | AD-1 | Matthew Merritt | Test case created for task AD-1 passes | 2021-11-19 |  | Completed
AD-3 | L | Find code that is controlling how long the fireballs last and when they are destroyed | 2 | 1.5 | AD-2 | Matthew Merritt | Test case created for task AD-1 passes | 2021-11-27 |  | Completed
AD-4 | L | Implement a fix to make the fireballs last for the full duration | 1 | 1 | AD-3 | Matthew Merritt | Test case created for task AD-1 passes | 2021-11-28 |  | Completed
AD-5 | L | Fill out test case | 0.25 | 0.25 | AD-4 | Dylan Widecki | Test case created for task AD-1 passes | 2021-11-29 |  | Completed
AL-1 | M - Attack Location Bug | Create Test Case | 0.25 | 0.25 | Team Discussion | Dylan Widecki | Test case is created and added to repository | 2021-11-18 |  | Completed
AL-2 | M | Go through test case | 0.25 | 0.25 | AL-1 | Dylan Widecki | Test case created for task AL-1 passes | 2021-11-19 |  | Completed
AL-3 | M | Find code associated with the players attack that determines its location in relation to the players location | 1 | 1 | AL-2 | Dylan Widecki | Test case created for task AL-1 passes | 2021-11-27 |  | Completed
AL-4 | M | Implement a fix to make the powerup display appropriately spaced from the player | 1 | 0.5 | AL-3 | Dylan Widecki | Test case created for task AL-1 passes | 2021-11-28 |  | Completed
AL-5 | M | Fill out test case | 0.25 | 0.25 | AL-4 | Emily Balboni | Test case created for task AL-1 passes | 2021-11-29 |  | Completed
LI-1 | N - Lives System Enhancement | Create Test Case | 0.25 | 0.25 | Team Discussion | Emily Balboni | Test case is created and added to repository | 2021-11-18 |  | Completed
LI-2 | N | Read Through Test Case | 0.25 | 0.25 | LI-1 | Emily Balboni | Test case created for task LI-1 passes | 2021-11-19 |  | Completed
LI-3 | N | Create and implement a visualization for how many lives the player has. | 1 | 0.5 | LI-2 | Emily Balboni | Test case created for task LI-1 passes | 2021-11-27 | When implementing the visualization, the hearts also appeared on the lose screen as it is classified as a level screen. In the end it was beneficial as it updated the user before they began the next level as to how many lives were left. | Completed
LI-4 | N | Read through code that deals with collisions of enemy and the player | 1 | 0.5 | LI-2 | Emily Balboni | Test case created for task LI-1 passes | 2021-11-27 |  | Completed
LI-5 | N | Create a holder class to store the number of lives a player has | 0.5 | 0.25 | LI-4 | Emily Balboni | Test case created for task LI-1 passes | 2021-11-28 |  | Completed
LI-6 | N | Update the holder appropriately throughout the code | 1 | 1 | LI-5 | Emily Balboni | Test case created for task LI-1 passes | 2021-11-28 | When first implementing the lives holder, there was a null pointer error. In the initializer method in the LevelLoseScreen class we had to add conditionals in order to fix it. | Completed
LI-7 | N | Implement code so when out of lives the user is taken back to the main menu | 0.5 | 0.25 | LI-5, LI-6 | Emily Balboni | Test case created for task LI-1 passes | 2021-11-28 |  | Completed
LI-8 | N | Fill out test case | 0.25 | 0.25 | LI-7 | Priscilla Esteves | Test case created for task LI-1 passes | 2021-11-29 |  | Completed
LS-1 | O - Level Select Enhancement | Create Test Case | 0.25 | 0.25 | Team Discussion | Priscilla Esteves | Test case is created and added to repository | 2021-11-18 |  | Completed
LS-2 | O | Go through Test Case | 0.25 | 0.25 | LS-1 | Priscilla Esteves | Test case created for task LS-1 passes | 2021-11-18 |  | Completed
LS-3 | O | Find code for loading levels and adding new screens | 1 | 1.5 | LS-2 | Priscilla Esteves | Test case created for task LS-1 passes | 2021-11-27 |  | Completed
LS-4 | O | Create a level selection screen with buttons | 1.5 | 1.5 | LS-3 | Priscilla Esteves, Matthew Merritt | Test case created for task LS-1 passes | 2021-11-27 |  | Completed
LS-5 | O | Fill out test case | 0.25 | 0.25 | LS-4 | Priscilla Esteves | Test case created for task LS-1 passes | 2021-11-28 |  | Completed
NL-1 | P - New Levels Enhancement | Create Test Case | 0.25 | 0.25 | Team Discussion | Amber Kusma | Test case is created and added to repository | 2021-11-18 |  | Completed
NL-2 | P | Read Through Test Case | 0.25 | 0.25 | NL-1 | Amber Kusma | Test case created for task NL-1 passes | 2021-11-18 |  | Completed
NL-3 | P | Create blank level files | 0.25 | 0.25 | NL-2 | Amber Kusma | Test case created for task NL-1 passes | 2021-11-20 |  | Completed
NL-4 | P | Implement code for new level 6 | 1.5 | 1.5 | NL-3 | Amber Kusma | Test case created for task NL-1 passes | 2021-11-28 |  | Completed
NL-5 | P | Implement code for new level 7 | 1.5 | 1.5 | NL-4 | Amber Kusma | Test case created for task NL-1 passes | 2021-11-28 |  | Completed
NL-6 | P | Fill out test case | 0.25 | 0.25 | NL-5 | Matthew Merritt | Test case created for task NL-1 passes | 2021-11-29 |  | Completed
SM-1 | n/a | Write Notable System Improvement | 0.5 | 0.5 | Backlog Items Selected | Matthew Merritt | Team and Manager sign document | 2021-11-16 |  | Completed
SM-2 | n/a | Merge Branches | 1 | 1.25 | AD-5, AL-5, LI-8, LS-5, NL-6 | Matthew Merritt | All active branches are merged into master branch | 2021-11-29 | A couple of branches needed some small bug fixes before being merged. | Completed
R-1 | n/a | Create Presentation Slides Individually | 1 | 1 | SM-2 | Whole Team | All slides are visible in the shared PowerPoint Presentation | 2021-12-01 |  | Completed
R-2 | n/a | Practice Presentation as Team | 1 | 1 | R-1 | Whole Team | Team completes at least two practice runs of the full presentation | 2021-12-01 |  | Completed
R-3 | n/a | Update Backlog | 0.5 | 0.5 | SM-2 | Matthew Merritt | Backlog contains all prioritized bugs and enhancements, and completed items are moved to a separate list | 2021-12-02 |  | Completed
R-3 | n/a | Write Individual Postmortems | 0.5 | 0.5 | Presentation | Whole Team | Postmortems meet requirements from the rubric and are visible in OneDrive | 2021-12-03 |  | Completed
R-4 | n/a | Write Team Postmortem | 0.5 | 0.5 | Presentation | Matthew Merritt | Postmortems meet requirements from the rubric and are visible in OneDrive | 2021-12-03 |  | Completed
|  | Total Times: | 23.5 | 21.75